## Plan
Nội dung công việc |  |  |  | Thời gian bắt đầu |  | Thời gian hoàn thành |  | Thời gian hoàn thành thực tế |  | Ghi chú
No | Module | Functions | Uu tiên | Ngày | Tháng | Ngày | Tháng | Ngày | Tháng
1 | Phân tích yêu cầu | - Mô tả yêu cầu - Gửi xác nhận - Chỉnh sửa và chốt lại phạm vi | 1 | 2 | 11 | 6 | 11
2 | Dựng môi trường | Thiết lập môi trường phát triển | 1 | 4 | 11 | 5 | 11
3 | Database | Thiết kế database | 1 | 6 | 11 | 8 | 11
4 | SMS client | Kết nối từ PC đến GSM modem hoặc Nokia 2730 | 3 | 18 | 11 | 19 | 11
5 |  | Kết nối SMS client đến GSM modem hoặc Nokia 2730 | 3 | 18 | 11 | 19 | 11
6 |  | Nhận và xử lý gửi tin giữa máy chủ và máy trạm | 4 | 20 | 11 | 26 | 11
|  | Messenger center settings | 2 | 9 | 11 | 12 | 11
7 |  | Disconnect (GSM modem or Nokia 2730) | 3 | 18 | 11 | 19 | 11
8 | Supper admin page | Dasboard | 11 | 18 | 12 | 24 | 12
9 |  | System settings | 10 | 18 | 12 | 24 | 12
10 |  | Account management | 2 | 9 | 11 | 12 | 11
11 |  | Account setting | 2 | 9 | 11 | 12 | 11
12 |  | Quản lý trạm/ Danh sách trạm | 4 | 20 | 11 | 26 | 11
13 |  | Quản lý trạm/ Báo cáo thống kê | 4 | 20 | 11 | 26 | 11
14 |  | Quản lý gửi tin/ Danh sách chờ | 5 | 27 | 11 | 3 | 12
15 |  | Quản lý gửi tin/ Màn hình gửi tin | 4 | 20 | 11 | 26 | 11
16 |  | Quản lý gửi tin/ Lịch sử gửi tin | 4 | 20 | 11 | 26 | 11
17 |  | Biểu đồ tin nhắn/ Sản lượng theo giờ | 6 | 4 | 12 | 10 | 12
18 |  | Biểu đồ tin nhắn/ Sản lượng theo ngày | 6 | 4 | 12 | 10 | 12
19 |  | Biểu đồ tin nhắn/ Sản lượng theo tháng | 6 | 4 | 12 | 10 | 12
20 |  | Biểu đồ tin nhắn/ Sản lượng theo năm | 6 | 4 | 12 | 10 | 12
21 |  | Biểu đồ tỷ lệ thành công | 7 | 4 | 12 | 10 | 12
|  | API tích hợp với phần mềm của khách hàng | 11 | 18 | 12 | 24 | 12
22 |  | Tài liệu API (Customer and Manager) | 11 | 18 | 12 | 24 | 12
23 | Admin page | Login | 2 | 13 | 11 | 17 | 11
24 |  | Profile | 2 | 13 | 11 | 17 | 11
25 |  | Setting | 3 | 18 | 11 | 19 | 11
26 |  | Dasboard | 11 | 18 | 12 | 24 | 12
27 |  | Quản lý trạm/ Danh sách trạm | 5 | 27 | 11 | 3 | 12
28 |  | Quản lý gửi tin/ Danh sách chờ | 5 | 27 | 11 | 3 | 12
29 |  | Biểu đồ tin nhắn/ Sản lượng theo giờ | 8 | 11 | 12 | 17 | 12
30 |  | Biểu đồ tin nhắn/ Sản lượng theo ngày | 8 | 11 | 12 | 17 | 12
31 |  | Biểu đồ tin nhắn/ Sản lượng theo tháng | 8 | 11 | 12 | 17 | 12
32 |  | Biểu đồ tin nhắn/ Sản lượng theo năm | 8 | 11 | 12 | 17 | 12
33 |  | Biểu đồ tỷ lệ thành công | 8 | 11 | 12 | 17 | 12
34 |  | Tài liệu API | 11 | 18 | 12 | 24 | 12
35 | Customer page | Login | 2 | 13 | 11 | 17 | 11
36 |  | Profile | 2 | 13 | 11 | 17 | 11
37 |  | Quản lý gửi tin/ Màn hình gửi tin | 5 | 27 | 11 | 3 | 12
38 |  | Quản lý gửi tin/ Lịch sử gửi tin | 5 | 27 | 11 | 3 | 12
39 |  | Biểu đồ tin nhắn/ Sản lượng theo giờ | 9 | 11 | 12 | 17 | 12
40 |  | Biểu đồ tin nhắn/ Sản lượng theo ngày | 9 | 11 | 12 | 17 | 12
41 |  | Biểu đồ tin nhắn/ Sản lượng theo tháng | 9 | 11 | 12 | 17 | 12
42 |  | Biểu đồ tin nhắn/ Sản lượng theo năm | 9 | 11 | 12 | 17 | 12
43 |  | Biểu đồ tỷ lệ thành công | 9 | 11 | 12 | 17 | 12
44 |  | Tài liệu API | 11 | 18 | 12 | 24 | 12
45 | System | Job chạy tự động | 10 | 18 | 12 | 24 | 12
46 | Triển khai và nghiệm thu | System testing | 12 | 18 | 12 | 24 | 12
47 |  | UAT | 12 | 25 | 12 | 31 | 12
48 |  | Golive | 12 | 1 | 01/2018 | 1 | 01/2018

## Requirement
No. | Module | Functions | Descriptions | Estimate (Mds) | API | Database | Supper Admin | Admin | Customer | System | Note
1 | Profile | Đăng nhập, Quên mật khẩu | Đăng nhập, Quên mật khẩu |  |  | Account_User | x | x | x
2 |  | Chỉnh sửa thông tin cá nhân | Chỉnh sửa thông tin cá nhân |  |  |  | x | x | x
3 |  | Đăng xuất | Đăng xuất |  |  |  | x | x | x
4 | Quản lý Menu | Quản lý menu | Tạo menu và các page tương ứng | [6 empty] | x
5 |  | Quản lý vai trò | Tạo các nhóm quyền: Super admin, Adin, Customer | [6 empty] | x
6 |  | Phân quyền | Phân quyền nhóm quyền theo: - Menu - Chi tiết từng tính năng | [6 empty] | x
7 | Dasboard | Dasboard | - Xem thông tin cần thông báo của hệ thống | 0.5 |  | System_Setting | x | x | x
8 |  |  | - Chỉnh sửa nội dung thông báo | 0.5 |  |  | x
9 | Quản lý hệ thống | Cài đặt hệ thống | Thời gian check connect tới các Trạm (VD: 40s) | 1 |  | System_Setting | x
11 |  |  | Chuỗi ký tự cần ghép, ngăn cách nhau bởi dấu phẩy |  |  |  | x
12 |  |  | Quy tắc ghép chuỗi |  |  |  | x
13 |  | Cài đặt nhà mạng | Cài đặt để tự động tách tin và kiểm soát đầu vào theo nhà mạng: - Thêm, Sửa 1 nhà mạng - Nhập số ký tự cần tách/ 1 SMS cho mỗi nhà mạng - Sửa đầu số cho phép với mỗi nhà mạng - Độ dài tối thiểu của 1 số hợp lệ của mỗi nhà mạng - Độ dài tối đa của 1 số hợp lệ Của mỗi nhà mạng | 1 |  | Carrier_Setting | x
19 |  | Người dùng | - Thêm mới tài khoản quản lý (SuperAdmin, Admin, Customer) | 2 |  | User_Account | x
20 |  |  | - Chỉnh sửa, xóa tài khoản |  |  |  | x
21 |  |  | - Tìm kiếm thông tin tài khoản |  |  |  | x
22 |  |  | - Phân quyền theo nhóm quyền |  |  |  | x
23 |  | Người dùng/ Cài đặt tài khoản admin | - Setting các thông số cần thiết cho tài khoản Manager: + Độ ưu tiên của admin + Hình thức thanh toán + Số dư tài khoản + Máy chủ tự động quét khi gửi SMS | 1 |  | User_Account, Manager_Setting | x
|  |  | - Cài đặt chi phí 1 SMS đươc nhận theo từng nhà mạng |  |  | Carrier_Setting, User_Account | x
|  | Người dùng/ Cài đặt tài khoản Customer | - Setting các thông số cần thiết cho tài khoản Customer: + Độ ưu tiên của khách hàng + Hình thức thanh toán + Số dư tài khoản + Tin được gửi tự động hay qua bước kiểm duyệt | 1 |  | User_Account, Customer_Setting | x
24 |  |  | - Cài đặt chi phí 1 SMS phải trả theo từng nhà mạng |  |  | Carrier_Setting, User_Account | x
57 | Quản lý Trạm | Cài đặt Trạm | Cài đặt việc phân bổ tin cho các COM: - Số lượng tin max có thể gửi trong 1 lần kết nối với COM - Số lần gửi lỗi tối đa trong 1 lần kết nối tới COM - Thời gian trễ giữa 2 lần gửi trên 1 COM từ - Thời gian trễ giữa 2 lần gửi trên 1 COM đến - Chuỗi ký tự cần ghép, ngăn cách nhau bởi dấu phẩy - Quy tắc ghép chuỗi |  |  | User_Account, Manager_Settings, Carrier_Setting |  | x
27 |  | Thống kê Trạm | - Hiển thị thông tin theo id của admin: + Tên modem + Tên admin + Số lượng gửi thành công, thất bại trong lần kết nối + Thời gian kết nối gần nhất + Thông số về Modem + Tình trạng kích hoạt (On/Off) |  |  | User_Account, Modem, Modem_Com | x
25 |  | Danh sách trạm | - Tìm kiếm danh sách trạm + Theo admin + Mức độ ưu tiên |  |  | User_Account, Device_Token, Modem, Modem_Com | x | x
26 |  |  | - Hiển thị danh sách com theo trạm theo id của admin: + Nhà mạng + Imei Com + Số lượng thành công, thất bại trong lần kết nối + Thời gian cập nhật gần nhất + Thông số về Com + Trang thái của Com (On/Off) |  |  |  | x | x
28 |  | SMS chờ xử lý | - Tìm kiếm: Theo khách hàng, thời gian, độ ưu tiên của khách hàng |  |  | System_Setting, User_Account, Customer_Setting, SMS_Customer, SMS_Log, SMS_SendTo | x
29 | Quản lý SMS |  | - Chỉnh sửa: Chỉnh sửa nội dung, thêm số lượng, cắt ký tự, chọn trạm xử lý |  |  |  | x
30 |  |  | - Truyền nội dung SMS đến máy trạm theo các thông số được thiết lập => Kiểm tra số SMS có thể gửi hiện tại để cảnh báo khả năng đáp ứng (Số SMS có thể gửi và tổng số lượng COM đang kích hoạt của Trạm) |  |  |  | x
66 |  | SMS chờ gửi | - Tìm kiếm: Theo thời gian |  |  | User_Account, Manager_Setting, SMS_Customer, SMS_Log, SMS_SendTo |  | x
67 |  |  | - Chỉnh sửa: Chỉnh sửa nội dung, Chọn file ký tự cần chèn * Note: Không chọn file sẽ lấy từ file cấu hình (gọi từ cấu hình) |  |  |  |  | x
68 |  |  | - Truyền nội dung SMS đến các COM theo các thông số được thiết lập => Kiểm tra số SMS có thể gửi hiện tại để cảnh báo khả năng đáp ứng theo danh sách COM được chọn và lượng tin cần gửi |  |  |  |  | x
31 |  | Màn hình gửi tin | - Màn hình gửi tin (Gửi trực tiếp trên giao diện của khách hàng): + Danh sách số điện thoại cần gửi + Nội dung tin nhắn (Có validate đầu vào) |  |  | System_Setting, User_Account, Customer_Setting, SMS_Customer, SMS_Log, SMS_SendTo | x |  | x
32 |  |  | - Đọc danh sách số điện thoại và nội dung từ file excel (Nếu không nhập cột nội dung thì lấy content được nhập vào) |  |  |  | x |  | x
|  | Gửi SMS thông qua API tích hợp với các hệ thống khác | - Viết API tích hợp với các phần mềm khác để nhận SMS: + Id kết nối + Id khách hàng + Danh sách số điện thoại cần gửi + Danh sách nội dung cần gửi | [6 empty] | x
33 |  | Quản lý gửi tin/ Lịch sử gửi tin | - Lọc theo khách hàng |  |  | User_Account, SMS_Customer | x |  | x
34 |  |  | - Hiển thị thông tin theo id của khách hàng: + id gói tin của khách hàng (sms_customer_id) + Ngày giờ gửi + Số lần gửi thành công + Số lần gửi thất bại + Số không hợp lệ + Chuỗi số không hợp lệ + Xem chi tiết |  |  |  | x |  | x
35 |  |  | - Xem danh sách chi tiết lịch sử theo lần gửi tin: + id gói tin của khách hàng (sms_customer_id) + Id gói tin được phân tách theo nhà mạng + Tên nhà mạng + Id tin được gửi + Số gửi đến + Ngày giờ gửi + Trang thái: Thành công, thất bại |  |  | User_Account, SMS_Customer, SMS_SendTo | x |  | x
36 |  | Biểu đồ tin nhắn/ Sản lượng theo giờ | - Thống kê theo admin |  |  | User_Account, Sms_Report | x | x
38 |  |  | - Hiển thị thông tin sản lượng theo giờ trong ngày dưới dạng biểu đồ (chia thành 8 khung giờ) |  |  |  | x | x
39 |  | Biểu đồ tin nhắn/ Sản lượng theo ngày | - Thống kê theo admin |  |  | User_Account, Sms_Report | x | x
40 |  |  | - Thống kê theo khách hàng |  |  |  | x | x
41 |  |  | - Hiển thị thông tin sản lượng theo ngày trong tháng dưới dạng biểu đồ |  |  | User_Account, Sms_Report | x | x
42 |  | Biểu đồ tin nhắn/ Sản lượng theo tháng | - Thống kê theo admin |  |  |  | x | x
43 |  |  | - Thống kê theo khách hàng |  |  | User_Account, Sms_Report | x | x
44 |  |  | - Hiển thị thông tin sản lượng theo tháng trong năm dưới dạng biểu đồ |  |  |  | x | x
45 |  | Biểu đồ tin nhắn/ Sản lượng theo năm | - Thống kê theo admin |  |  | User_Account, Sms_Report | x | x
46 |  |  | - Thống kê theo khách hàng |  |  |  | x | x
47 |  |  | - Hiển thị thông tin sản lượng theo năm dưới dạng biểu đồ (3 năm gần nhất) |  |  |  | x | x
48 |  | Biểu đồ tỷ lệ thành công | - Lọc theo Nhà mạng, tháng, năm |  |  | User_Account, Sms_Report | x | x
49 |  |  | - Lọc theo admin |  |  |  | x | x
50 |  |  | - Lọc theo khách hàng |  |  |  | x | x
51 |  |  | - Thống kê theo ngày |  |  |  | x | x
| Tài liệu API | API kết nối trạm | Xem thông tin kết nối Trạm |  |  | System_Setting | x | x
|  |  | Sửa thông tin kết nối Trạm |  |  |  | x
|  | API tích hợp | Xem thông tin kết nối Hệ thống của khách hàng |  |  |  | x |  | x
53 |  |  | Sửa thông tin kết nối Hệ thống của khách hàng |  | 0.5 |  | x
1 | SMS client | Connect | Kết nối PC – GSM Modem qua cổng USB | 2 |  | User_Account, Modem, Modem_Com |  | x |  | x | Sử dụng phần mềm CDM20828 theo Id của tài khoản admin
2 |  |  | Kết nối PC – Điện thoại Nokia 2730 qua cổng USB
3 |  | Kết nối SMS client với Modem | - Kết nối tới máy chủ - Truyền trạng thái On/Off của các Com - Truyền Số lượng Trạm và Số lượng Com được kết nối | 2 |  | User_Account, Modem, Modem_Com, Device_Token |  | x |  | x
4 |  | Nhận và xử lý gửi tin | - Nhận thông tin SMS cần gửi tin - Điều khiển để gửi tin (Com phải đảm bảo: Không quá số lần gửi lỗi cho phép, không vượt quá số tin max trong ngày) - Truyền trạng thái gửi "Thành công" hay "Thất bại" lên máy chủ | 10 |  |  | x | x |  | x
[7 empty] | x | x |  | x
[7 empty] | x | x |  | x
[7 empty] | x | x |  | x
[7 empty] | x | x |  | x
[7 empty] | x | x |  | x
|  | Check delay giữa các lần gửi trong 1 COM |  | 4 | [5 empty] | x
5 |  | Settings | Cài đặt trung tâm tin nhắn: - Chọn default từ sim - Nhập vào 1 hoặc nhiều trung tâm tin nhắn | 5 |  | SMS Client (App winform) |  | x
6 |  | Disconnect | - Toàn bộ số lượng Com đã kết nối sẽ chuyển trạng thái OFF '- Reset lại trường "sms_error_max" về 0 khi ngắt kết nối | 2 |  | User_Account, Modem, Modem_Com, Device_Token |  | x |  | x
98 | System | Job chạy tự động | Reset lại trường "sms_max_com_day" về 0 và cuối ngày trong bảng "Modem_Com" với các Com đang hoạt động | [6 empty] | x
99 |  |  | Reset lại trường "sms_max_day về 0 trong bảng "Manager_Settings" | [6 empty] | x
100 |  |  | Check connect với các trạm theo time được set | [6 empty] | x

## DB
TABLE "Administrator"
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | Mã tài khoản Supper admin
2 | full_name | varchar | 50 | NOTNULL | Họ và tên
3 | email | varchar | 255 | NOTNULL | Địa chỉ email (Làm tài khoản đăng nhập)
4 | password | varchar | 255 | NOTNULL | Mật khẩu (Mã hóa MD5)
5 | created_date | datetime |  | NOTNULL | Ngày khởi tạo (ngày hệ thống)
6 | updated_date | datetime |  | NULL | Ngày update (ngày hệ thống)
PRIMARY KEY ("id")
TABLE "Device_Token"
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | Mã của com trong modem
2 | manager_id | bigint | 8 | NOTNULL | Liên kết với id trong table "Manager"
3 | device_id | bigint | 8 | NOTNULL | id của thiết bị (PC) connect tới hệ thống
4 | token | bigint | 8 | NOTNULL | token của thiết bị (PC) được connect tới hệ thống
5 | messeger_center | varchar | 255 | NOTNULL | Trung tâm tin nhắn: - Ngăn cách nhau bởi dấu phẩy - Màn hình nhập cho phép chọn default từ sim - Hoặc nhập vào 1 hoặc nhiều trung tâm tin nhắn
6 | status | int | 2 | NOTNULL | Tình trạng hoạt động (1 - on; 0 - off)
7 | created_date | datetime |  | NOTNULL | Thời gian tạo lần đầu
8 | updated_date | datetime |  | NULL | Thời gian cập nhật gần nhất
PRIMARY KEY ("id")
TABLE "System_Setting"
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | id thiết lập hệ thống
2 | time_check_connect | bigint | 8 | NOTNULL | Thiết lập thời gian hệ thống tự động kiểm tra kết nối tới các trạm | menu "Cài hệ thống"
3 | concatenation_strings | text |  | NOTNULL | Chuỗi ký tự cần ghép, ngăn cách nhau bởi dấu phẩy | menu "Cài hệ thống"
4 | concatenation_rule | bigint | 8 | NOTNULL | 1- Đầu; 2 - Cuối; 3 - Vị trí giữa radom bất kỳ trong chuỗi | menu "Cài hệ thống"
5 | api_manager | text |  | NOTNULL | Nội dung mô tả kết nội API của admin | menu "Tài liệu API" => để hiển thị trên màn hình Customer
6 | api_manager_en | text |  | NOTNULL | Nội dung mô tả kết nội API của admin (Tiếng anh) | menu "Tài liệu API"
7 | api_customer | text |  | NOTNULL | Nội dung mô tả kết nội API của khách hàng | menu "Tích hợp API" => để hiển thị trên màn hình Admin
8 | api_customer_en | text |  | NOTNULL | Nội dung mô tả kết nội API của khách hàng (Tiếng anh) | menu "Tích hợp API"
9 | system_content | text |  | NOTNULL | Thông báo từ hệ thống | menu "Bảng điều khiển"
10 | system_content_en | text |  | NOTNULL | Thông báo từ hệ thống (Tiếng anh) | menu "Bảng điều khiển"
11 | created_date | datetime |  | NOTNULL | Thời gian tạo lần đầu
12 | updated_date | datetime |  | NULL | Thời gian cập nhật gần nhất
PRIMARY KEY ("id")
TABLE "Carrier_Setting"
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | id nhà mạng
2 | carrier_name | varchar | 50 | NULL | Tên nhà mạng tương ứng
3 | slipt_number | bigint | 8 | NOTNULL | Số ký tự cần tách
4 | first_number | varchar | 100 | NOTNULL | Danh sách các đầu số cho phép, nhập cách nhau bởi dấu phẩy
5 | min_number | bigint | 8 | NOTNULL | Độ dài tối thiểu của 1 số hợp lệ
6 | max_number | bigint | 8 | NOTNULL | Độ dài tối đa của 1 số hợp lệ
7 | status |  |  |  | Ẩn, Hiện
8 | created_date | datetime |  | NOTNULL | Thời gian tạo lần đầu
9 | updated_date | datetime |  | NULL | Thời gian cập nhật gần nhất
PRIMARY KEY ("id")
TABLE "User_Account"
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | id tài khoản đăng nhập
2 | role_type | varchar | 200 | NULL | Loại tài khoản: 0,1,2
3 | role_name | varchar | 50 | NOTNULL | Tên tài khoản tương ứng: SuperAdmin, Admin, Customer
4 | full_name | varchar | 50 | NOTNULL | Họ và tên
5 | email | varchar | 255 | NOTNULL | Địa chỉ email (Làm tài khoản đăng nhập)
6 | password | varchar | 100 | NOTNULL | Mật khẩu (Mã hóa MD5)
7 | sex | tinyint | 2 | NULL | Giới tính
8 | birthday | date |  | NULL | Ngày sinh
9 | telephone | varchar | 200 | NULL | Số điện thoại cố định
10 | mobile | varchar | 200 | NULL | Số điện thoại di động
11 | is_active | tinyint | 2 | NOTNULL | Tình trạng tài khoản (1 On, 0 Off)
10 | address | varchar | 255 | NULL | Địa chỉ
11 | number | varchar | 50 | NULL | Số giấy phép kinh doanh
12 | address_register | varchar | 255 | NULL | Địa chỉ đăng ký
18 | created_date | datetime |  | NOTNULL | Ngày khởi tạo (ngày hệ thống)
19 | updated_date | datetime |  | NULL | Ngày update (ngày hệ thống)
PRIMARY KEY ("id")
TABLE "Manager_Setting"
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | id setting cho 1 admin
2 | manager_id | bigint | 8 | NOTNULL | Liên kết với id của bảng User_Account với Role_Type = 1
4 | priority | tinyint | 2 | NULL | Độ ưu tiên của admin | Supper admin
5 | payment_type | tinyint | 2 | NULL | Hình thức thanh toán: 1 - Thanh toán trực tiếp; 2 - Thanh toán sau | Supper admin
6 | account_balance | float | 8 | NULL | Số dư trong tài khoản | Supper admin
7 | scan_auto | tinyint | 2 | NOTNULL | Máy chủ tự động quét gửi SMS (1 có; 0 không) | Supper admin
8 | count_sms_number | tinyint | 2 | NOTNULL | Đếm số lượng tin đã gửi trong ngày, tự tăng khi truyền thành công gói tin về Trạm (Cuối ngày sẽ reset về 0) | Supper admin
9 | sms_max | bigint | 8 | NOTNULL | Số lượng tin max có thể gửi trong ngày theo COM | Admin
10 | sms_error_max | tinyint | 8 | NOTNULL | Số lần gửi lỗi tối đa trong 1 lần kết nối tới COM | Admin
11 | time_delay_from | tinyint | 8 | NOTNULL | Thời gian trễ giữa 2 lần gửi trên 1 COM từ | Admin
12 | time_delay_to | tinyint | 8 | NOTNULL | Thời gian trễ giữa 2 lần gửi trên 1 COM đến | Admin
13 | concatenation_strings | text |  | NOTNULL | Chuỗi ký tự cần ghép, ngăn cách nhau bởi dấu phẩy | Admin
14 | concatenation_rule | bigint | 8 | NOTNULL | 1- Đầu; 2 - Cuối; 3 - Vị trí thứ n trong chuỗi (n cho nhập); 4 - Vị trí giữa bất kỳ trong chuỗi | Admin
15 | created_date | datetime |  | NOTNULL | Ngày khởi tạo (ngày hệ thống)
16 | updated_date | datetime |  | NULL | Ngày update (ngày hệ thống)
PRIMARY KEY ("id")
TABLE "Customer_Setting"
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | id setting cho 1 khách hàng
2 | manager_id | bigint | 8 | NOTNULL | Liên kết với id của bảng User_Account với Role_Type = 2
3 | priority | tinyint | 2 | NULL | Độ ưu tiên của khách hàng
4 | payment_type | tinyint | 2 | NULL | Hình thức thanh toán: 1 - Thanh toán trước; 2 - Thanh toán sau
5 | account_balance | float |  | NULL | Số dư trong tài khoản
6 | sms_send_auto | tinyint | 2 | NOTNULL | Tin sẽ được gửi tự động hoặc qua bước kiểm duyệt (1 - tự động; 0 - Qua kiểm duyêt)
7 | created_date | datetime |  | NOTNULL | Ngày khởi tạo (ngày hệ thống)
8 | updated_date | datetime |  | NULL | Ngày update (ngày hệ thống)
PRIMARY KEY ("id")
TABLE "User_Carrier_Setting"
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | id setting cho 1 admin
2 | carrier_id | bigint | 8 | NOTNULL | Liên kết với id của bảng Carrier_Setting
3 | manager_id | bigint | 8 | NULL | Liên kết với id của bảng User_Account với Role_Type = 1
4 | customer_id | bigint | 8 | NULL | Liên kết với id của bảng User_Account với Role_Type = 2
5 | cost | float |  | NULL | Chi phí cho 1 tin cài đặt theo từng admin hoặc customer
6 | created_date | datetime |  | NOTNULL | Ngày khởi tạo (ngày hệ thống)
7 | updated_date | datetime |  | NULL | Ngày update (ngày hệ thống)
PRIMARY KEY ("id")
TABLE "Modem" | [5 empty] | thêm bảng lưu tin nhắn theo từng mức
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | Mã của modem | Thêm bảng đếm số lượng gửi thành công, thất bại theo giờ, tháng, năm
2 | manager_id | bigint | 8 | NOTNULL | Liên kết với id của bảng User_Account với Role_Type = 1
3 | device_id | bigint | 8 | NOTNULL | Liên kết với trường "device_id trong bảng Device-Token
4 | name | varchar | 50 | NOTNULL | Ký danh của modem
5 | digital | varchar | 255 | NOTNULL | Thông số kỹ thuật của modem
6 | is_active | tinyint | 2 | NOTNULL | Tình trạng kích hoạt của modem (1- on; 0 off)
7 | created_date | datetime |  | NOTNULL | Ngày khởi tạo (ngày hệ thống)
8 | updated_date | datetime |  | NULL | Ngày update (ngày hệ thống)
PRIMARY KEY ("id")
TABLE "Modem_com"
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | Mã của com trong modem
2 | manager_id | bigint | 8 | NOTNULL | Liên kết với id của bảng User_Account với Role_Type = 1
3 | modem_id | bigint | 8 | NOTNULL | Liên kết với id trong table "Modem"
4 | name | varchar | 50 | NOTNULL | Tên của Com
5 | carrier_id | bigint | 8 | NOTNULL | Mã nhà mạng (0: Không xác định)
6 | carrier_name | varchar | 50 | NULL | Tên nhà mạng tương ứng (0: Không xác định)
7 | mei_com | varchar | 50 | NOTNULL | Thông số kỹ thuật của Com
8 | content | varchar | 255 | NOTNULL | Nội dung cảnh báo
9 | sms_max_com_day | tinyint | 8 | NOTNULL | Đếm số tin gửi thành công trong ngày để so sánh với số tối đa cho phép gửi (Cuối ngày sẽ reset về 0)
10 | success_number | tinyint | 2 | NOTNULL | Số lần gửi thành công trong 1 lần kết nối
11 | error_number | tinyint | 2 | NOTNULL | Số lần gửi lỗi trong 1 lần kết nối => Khi Com disconnect thì reset về 0
12 | is_active | tinyint | 2 | NOTNULL | Tình trạng kích hoạt của Com (1- on; 0 off; 2 - error) * note: error_number = sms_error_max (theo Manager_Settings) => update is_active = 2
13 | created_date | datetime |  | NOTNULL | Thời gian kích hoạt lần đầu
14 | updated_date | datetime |  | NULL | Thời gian kích hoạt lần cuối
PRIMARY KEY ("id")
TABLE "Sms_Customer"
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | id của 1 lần gửi sms | Số hợp lệ sẽ tách để insert ra bảng "Sms_Log"
2 | customer_id | bigint | 8 | NOTNULL | Liên kết với id của bảng User_Account với Role_Type = 2
3 | com_id | bigint | 8 | NOTNULL | Liên kết với id trong table "Com"
4 | correct_number | bigint | 8 | NOTNULL | Tổng số lượng số hợp lệ
5 | incorrect_number | bigint | 8 | NOTNULL | Tổng số lượng số không hợp lệ
6 | incorrect_number_list | text |  | NOTNULL | Chuỗi số không hợp lệ, ngăn cách bởi dấu phẩy
7 | status | int | 2 | NOTNULL | Tình trạng gói tin: 0; 1
8 | status_name | varchar | 10 | NOTNULL | Tương ứng status: Pending, Successful
9 | send_date | bigint | 8 | NOTNULL | Thời gian tạo bản ghi lịch sử gửi tin (yyyymmdd)
10 | created_date | datetime |  | NOTNULL | Thời gian tạo bản ghi lịch sử gửi tin
PRIMARY KEY ("id")
TABLE "Sms_Log"
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | id của 1 lần gửi sms | Chi tiết sẽ được tách trong bảng "Sms_SendTo"
6 | customer_id | bigint | 8 | NOTNULL | Liên kết với id của bảng User_Account với Role_Type = 2
2 | sms_customer_id | bigint | 8 | NOTNULL | id gói tin gốc, liên kết với id bảng "Sms_Customer"
3 | carrier_id | bigint | 8 | NOTNULL | Mã nhà mạng (0: Không xác định)
4 | carrier_name | varchar | 50 | NOTNULL | Tên nhà mạng tương ứng (0: Không xác định)
5 | manager_id | bigint | 8 | NULL | Liên kết với id của bảng User_Account với Role_Type = 1
6 | total_sms | bigint |  | NULL | Tổng số SMS cần gửi sau khi được tách theo từng nhà mạng
8 | send_sussesssful | bigint | 8 | NULL | Đếm số lần gửi thành công
9 | send_fail | bigint | 8 | NULL | Đếm số lần gửi thất bại
10 | sms_max | bigint | 8 | NULL | Tổng số sms gửi để check số lương max trong lần kế nối, trong ngày
11 | status | int | 2 | NOTNULL | Tình trạng gói tin: 0; 1
12 | status_name | varchar | 10 | NOTNULL | Tương ứng status: Pending, Successful
13 | send_date | bigint | 8 | NOTNULL | Thời gian tạo bản ghi lịch sử gửi tin (yyyymmdd)
14 | created_date | datetime |  | NOTNULL | Thời gian tạo bản ghi lịch sử gửi tin
PRIMARY KEY ("id")
TABLE "Sms_SendTo"
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | Mã của com trong modem
2 | sms_log_id | bigint | 8 | NULL | id gói tin sau khi được tách, liên kết với id trong table "Sms_Log"
3 | sms_customer_id | bigint | 8 | NULL | id gói tin gốc, liên kết với id bảng "Sms_Customer"
4 | customer_id | bigint | 8 | NOTNULL | Liên kết với id của bảng User_Account với Role_Type = 1
5 | carrier_id | bigint | 8 | NOTNULL | Mã nhà mạng (0: Không xác định)
6 | manager_id | bigint | 8 | NULL | Liên kết với id của bảng User_Account với Role_Type = 2
7 | modem_id | bigint | 8 | NULL | Liên kết với id trong table "Modem"
8 | com_id | bigint | 8 | NULL | Liên kết với id trong table "Com"
9 | phone_receive | varchar | 20 | NULL | Số điện thoại nhận
12 | phone_send | varchar | 20 | NOTNULL | Số điện thoại gửi
10 | status | int | 2 | NOTNULL | Tình trạng gửi tin: 0; 1; 2
11 | status_name | varchar | 10 | NOTNULL | Tương ứng status: Pending, Success, Fail
13 | content | varchar | 160 | NOTNULL | Nội dung của SMS
14 | hour | bigint | 8 | NOTNULL | Giờ gửi
15 | day | bigint | 8 | NOTNULL | Ngày gửi
16 | month | bigint | 8 | NOTNULL | Tháng gửi
17 | year | bigint | 8 | NOTNULL | Năm gửi
18 | send_date | bigint | 8 | NOTNULL | Thời gian gửi tin (yyyymmdd)
19 | created_date | datetime |  | NOTNULL | Thời gian gửi tin
PRIMARY KEY ("id")
TABLE "Sms_Report"
No. | Field name | Type | Length | Require | Note
1 | id | bigint | 8 | NOTNULL | Mã của 1 lần ghi log báo cáo
2 | customer_id | bigint | 8 | NOTNULL | Liên kết với id của bảng User_Account với Role_Type = 1
3 | manager_id | bigint | 8 | NOTNULL | Liên kết với id của bảng User_Account với Role_Type = 2
4 | carrier_id | bigint | 8 | NOTNULL | Liên kết với id trong table "Carrier_Setting"
5 | success_number | varchar | 20 | NOTNULL | Đếm số lượng gửi thành công theo giờ
6 | fail_number | varchar | 20 | NOTNULL | Đếm số lượng gửi thất bại theo giờ
7 | hour | bigint | 8 | NOTNULL | Giờ gửi
8 | day | bigint | 8 | NOTNULL | Ngày gửi
9 | month | bigint | 8 | NOTNULL | Tháng gửi
10 | year | bigint | 8 | NOTNULL | Năm gửi
11 | created_date | datetime |  | NOTNULL | Thời gian tạo bản ghi báo cáo
PRIMARY KEY ("id")

## Question
No. | Question | Answer
1 | Mỗi nhà Trạm sẽ chọn thêm bớt ký tự riêng, chia cắt số ký tự riêng hay theo nhà mạng | Tất cả các nhà mạng chọn chung được 1 chuỗi ký tự cần ghép
2 | Số ký tự được thêm ở đầu hay cuối đôạn ký tự được cắt | Cấu hình: Đầu, cuối, 1 vị trí bất kỳ hoặc random
3 | Số lượng tin Supper admin truyền về vượt quá năng lực của 1 trạm thì có cơ chế trả lại máy chủ để phân tải cho trạm khác không | Cài đặt số lượng tối đa trên 1 trạm chỉ cho phép
4 | Sau khi đã lọc ra danh sách số điện thoại hợp lệ. Gửi 1000 tin, lúc nào gửi được hết mới báo Done hay gửi 1000 lần | Số không tồn tại thì vẫn coi là thành công và ko check đc tình huống từ nhà mạng
5 | Việc cắt số ký tự/ tin có cho phép admin làm không vì ảnh hưởng đến chi phí hay chỉ cho phép tại quyền Supper admin | - Super admin sẽ cài đặt việc cắt số ký tự '- Trung tâm tin nhắn => đưa vào cài đặt nhà mạng '- Client setup thông số trung tâm tin nhắn: nhập tay hoặc tự động lấy trung tâm nhắn tin của nhà mạng
6 | Mỗi một nhà mạng có nguyên tắc chèn file khác nhau hay đều có thể dùng chung được | => chuỗi dùng chung
7 | Chuỗi tin nhắn nhận từ khách hàng hiện tại nếu không hợp lệ có xử lý không hay mặc định vẫn gửi bình thường | supper admin sẽ duyệt và sửa
8 | Thời gian giữa mỗi lần gửi tin sao không để 1 giá trị mà lại là Radom trong 1 khoảng từ X giây đến Y giây | Việc radom số giây từ x đến y để hách nhà mạng hiểu con người đang thao tác
9 | 2 PC khác nhau cùng connect 1 tài khoản thì ghi nhận cả 2 | OK. Hiển thị tất cả các Trạm được kết nối
10 | Có áp dụng cách trèn chuỗi tự động để gửi tin theo từng khách hàng được không | Hiện tại thì không dùng đến việc gửi tự động này. Vẫn settings

## Parent_Mgt_Edit (hidden)
1. Màn hình gán học sinh cho phụ huynh
| No. | 日本 | ベトナム語 | 英語 | Key language | Database
| 1 | 送迎登録 | Đăng ký đưa đón | Register pickup | register_pickup | eye_user_account
| * Note: | Thêm trường "register_pickup" trong bảng "eye_user_account"
Màn hình Quản lý học sinh:
=> Kích hoạt tài khoản phụ huynh => Tạo liên kết trong bảng eye_user_account trường "register_pickup" = 1
Màn hình Quản lý phụ huynh:
=> Sau khi chọn học sinh: Hiển thị luôn thông tin học sinh trên màn hình danh sách, mặc định trường "Đăng ký đưa đón" = 0
=> Tích chọn hoặc bỏ tích chọn => Lưu thông tin vào bảng eye_user_account
Màn hình "Điểm danh" (Trang quản trị và trang Giáo viên):
=> Danh sách người đưa đón: Đổi logic lọc phụ huynh có liên kết với học sinh trong bảng eye_user_account, trường "register_pickup" = 1

## Transportation_Mgt (hidden)
1. Màn hình thêm mới Chỉnh sửa xem đưa, xe đón
| No. | 日本 | ベトナム語 | 英語 | Key language | Database
1
2
3
4
5
6
7
8
9
10

## DB_All (hidden)
CREATE TABLE "eye_sys"."agent" ( | CREATE TABLE "eye_sys"."log_update" ( | CREATE TABLE "eye_sys"."site Copy 1" (
id bigint NOT NULL, | id bigint NOT NULL, | id bigint NOT NULL,
name varchar(255) CHARACTER SET utf8 NOT NULL, | table_name varchar(50) CHARACTER SET utf8 NOT NULL, | members_id bigint NOT NULL,
tel varchar(20) CHARACTER SET utf8 NOT NULL, | rec_id bigint NOT NULL, | site_name varchar(255) CHARACTER SET utf8 NOT NULL,
zip varchar(10) CHARACTER SET utf8 NOT NULL, | updated_at datetime NOT NULL, | sub_title varchar(255) CHARACTER SET utf8 NOT NULL,
area int NOT NULL, | updater_type int NOT NULL, | tel varchar(50) CHARACTER SET utf8 NOT NULL,
address varchar(255) CHARACTER SET utf8 NOT NULL, | updater_table varchar(50) CHARACTER SET utf8 NOT NULL, | address varchar(255) CHARACTER SET utf8 NOT NULL,
note text CHARACTER SET utf8 NOT NULL, | updater_id int NOT NULL, | site_url varchar(255) CHARACTER SET utf8 NOT NULL,
intro_kbn int NOT NULL, | updater_name varchar(50) CHARACTER SET utf8 NOT NULL, | url_status int NOT NULL,
is_fee tinyint NOT NULL, | PRIMARY KEY ("id") | description text CHARACTER SET utf8 NOT NULL,
created_at date NOT NULL, | ); | keyword varchar(255) CHARACTER SET utf8 NOT NULL,
PRIMARY KEY ("id") |  | template_id bigint NOT NULL,
); |  | theme_no int NOT NULL 1,
| CREATE TABLE "eye_sys"."manager" ( | mail_to varchar(100) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."blog" ( | id int NOT NULL 0, | is_ses tinyint NOT NULL,
id bigint NOT NULL, | name varchar(50) CHARACTER SET utf8 NOT NULL, | ses_name varchar(50) CHARACTER SET utf8 NOT NULL,
site_type int NOT NULL, | manage_id varchar(15) CHARACTER SET utf8 NOT NULL, | ses_mail varchar(255) CHARACTER SET utf8 NOT NULL,
date datetime NOT NULL, | password varchar(255) CHARACTER SET utf8 NOT NULL, | price int NOT NULL,
subject varchar(255) CHARACTER SET utf8 NOT NULL, | pages varchar(255) CHARACTER SET utf8 NOT NULL, | limit_date date NOT NULL,
category_id int NOT NULL, | level int NOT NULL 0, | settlement_status int NOT NULL,
body text CHARACTER SET utf8 NOT NULL, | is_delete tinyint NOT NULL, | is_sample tinyint NOT NULL,
file varchar(20) CHARACTER SET utf8 NOT NULL, | created_at datetime NOT NULL '0000-00-00 00:00:00', | is_developer tinyint NOT NULL,
is_important tinyint NOT NULL, | updated_at datetime NOT NULL '0000-00-00 00:00:00', | is_vip tinyint NOT NULL,
is_top tinyint NOT NULL, | PRIMARY KEY ("id") | system_option varchar(255) CHARACTER SET utf8 NOT NULL,
is_facebook tinyint NOT NULL, | ); | default_manage int NOT NULL,
is_release tinyint NOT NULL, |  | lang int NOT NULL,
created_at datetime NOT NULL, |  | use_lang varchar(255) CHARACTER SET utf8 NOT NULL,
manage_id int NOT NULL, | CREATE TABLE "eye_sys"."members" ( | is_release tinyint NOT NULL,
PRIMARY KEY ("id") | id int NOT NULL, | is_delete tinyint NOT NULL,
); | company varchar(255) CHARACTER SET utf8 NOT NULL, | payment_id varchar(50) CHARACTER SET utf8 NOT NULL,
| name varchar(50) CHARACTER SET utf8 NOT NULL, | delete_date date NOT NULL,
| kana varchar(50) CHARACTER SET utf8 NOT NULL, | created_at datetime NOT NULL,
CREATE TABLE "eye_sys"."designers" ( | mail varchar(255) CHARACTER SET utf8 NOT NULL, | updated_at datetime NOT NULL,
id bigint NOT NULL, | paypal_mail varchar(255) CHARACTER SET utf8 NOT NULL, | manage_id varchar(15) CHARACTER SET utf8 NOT NULL,
brand_name varchar(255) CHARACTER SET utf8 NOT NULL, | subscr_id varchar(255) CHARACTER SET utf8 NOT NULL, | PRIMARY KEY ("id")
file varchar(20) CHARACTER SET utf8 NOT NULL, | tel varchar(20) CHARACTER SET utf8 NOT NULL, | );
name varchar(255) CHARACTER SET utf8 NOT NULL, | zip varchar(10) CHARACTER SET utf8 NOT NULL,
kana varchar(255) CHARACTER SET utf8 NOT NULL, | area int NOT NULL,
mail varchar(255) CHARACTER SET utf8 NOT NULL, | address varchar(255) CHARACTER SET utf8 NOT NULL, | CREATE TABLE "eye_sys"."site_ Copy 1" (
paypal_mail varchar(255) CHARACTER SET utf8 NOT NULL, | password varchar(255) CHARACTER SET utf8 NOT NULL, | id bigint NOT NULL,
tel varchar(20) CHARACTER SET utf8 NOT NULL, | note text CHARACTER SET utf8 NOT NULL, | master_id bigint NOT NULL,
zip varchar(10) CHARACTER SET utf8 NOT NULL, | introduction_id bigint NOT NULL, | logo_file varchar(20) CHARACTER SET utf8 NOT NULL,
area int NOT NULL, | introduction_type int NOT NULL, | sns_bt varchar(255) CHARACTER SET utf8 NOT NULL,
address varchar(255) CHARACTER SET utf8 NOT NULL, | introduction_kbn int NOT NULL, | sp_nav_type int NOT NULL 1,
sex int NOT NULL, | txn_type varchar(20) CHARACTER SET utf8 NOT NULL, | info_is_release tinyint NOT NULL 1,
birthday date NOT NULL, | is_active tinyint NOT NULL, | info_name varchar(255) CHARACTER SET utf8 NOT NULL,
url varchar(255) CHARACTER SET utf8 NOT NULL, | is_withdraw tinyint NOT NULL, | info_label varchar(255) CHARACTER SET utf8 NOT NULL '1=>2,2=>2,3=>1,4=>1,5=>1,6=>1,7=>0',
comment text CHARACTER SET utf8 NOT NULL, | withdraw_date datetime NOT NULL, | info_form_comment text CHARACTER SET utf8 NOT NULL,
pr text CHARACTER SET utf8 NOT NULL, | is_delete tinyint NOT NULL, | info_complete_comment text CHARACTER SET utf8 NOT NULL,
note text CHARACTER SET utf8 NOT NULL, | delete_date datetime NOT NULL, | info_mail_subject varchar(255) CHARACTER SET utf8 NOT NULL,
password varchar(255) CHARACTER SET utf8 NOT NULL, | created_at datetime NOT NULL, | info_mail_body text CHARACTER SET utf8 NOT NULL,
disp_name tinyint NOT NULL, | updated_at datetime NOT NULL, | recruit_is_release tinyint NOT NULL,
disp_sex tinyint NOT NULL, | manage_id varchar(15) CHARACTER SET utf8 NOT NULL, | recruit_name varchar(255) CHARACTER SET utf8 NOT NULL,
disp_birthday tinyint NOT NULL, | PRIMARY KEY ("id") | recruit_label varchar(255) CHARACTER SET utf8 NOT NULL '1=>0,2=>2,3=>2,4=>2,5=>2,6=>2,7=>2,8=>2,9=>2,10=>2,11=>2,12=>1,13=>1,14=>1,15=>1,16=>1,17=>1',
introduction_id bigint NOT NULL, | ); | recruit_form_comment text CHARACTER SET utf8 NOT NULL,
is_withdraw tinyint NOT NULL, |  | recruit_complete_comment text CHARACTER SET utf8 NOT NULL,
withdraw_date datetime NOT NULL, |  | recruit_mail_subject varchar(255) CHARACTER SET utf8 NOT NULL,
is_delete tinyint NOT NULL, | CREATE TABLE "eye_sys"."members_site_master" ( | recruit_mail_body text CHARACTER SET utf8 NOT NULL,
delete_date datetime NOT NULL, | id bigint NOT NULL, | mmg_is_release tinyint NOT NULL,
is_first_time tinyint NOT NULL 1, | members_id bigint NOT NULL, | mmg_name varchar(255) CHARACTER SET utf8 NOT NULL,
created_at datetime NOT NULL, | site_name varchar(255) CHARACTER SET utf8 NOT NULL, | mmg_label varchar(255) CHARACTER SET utf8 NOT NULL '1=>1,2=>1,3=>1,4=>1',
updated_at datetime NOT NULL, | sub_title varchar(255) CHARACTER SET utf8 NOT NULL, | mmg_form_comment text CHARACTER SET utf8 NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, | site_url varchar(255) CHARACTER SET utf8 NOT NULL, | mmg_complete_comment text CHARACTER SET utf8 NOT NULL,
is_manager tinyint NOT NULL, | url_status int NOT NULL, | mmg_subject varchar(255) CHARACTER SET utf8 NOT NULL,
PRIMARY KEY ("id") | description text CHARACTER SET utf8 NOT NULL, | mmg_body text CHARACTER SET utf8 NOT NULL,
); | keyword varchar(255) CHARACTER SET utf8 NOT NULL, | policy_privacy text CHARACTER SET utf8 NOT NULL,
| template_id bigint NOT NULL, | copyright varchar(255) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."designers_news" ( | mail_info varchar(100) CHARACTER SET utf8 NOT NULL, | slider_effect varchar(20) CHARACTER SET utf8 NOT NULL,
id bigint NOT NULL, | limit_date date NOT NULL, | access_code text CHARACTER SET utf8 NOT NULL,
date datetime NOT NULL, | settlement_status int NOT NULL, | map_address varchar(255) CHARACTER SET utf8 NOT NULL,
comment text CHARACTER SET utf8 NOT NULL, | is_sample tinyint NOT NULL, | facebook_id varchar(50) CHARACTER SET utf8 NOT NULL,
link varchar(255) CHARACTER SET utf8 NOT NULL, | is_vip tinyint NOT NULL, | is_bilingual tinyint NOT NULL,
is_release tinyint NOT NULL, | is_release tinyint NOT NULL, | eye_year int NOT NULL,
created_at datetime NOT NULL, | is_delete tinyint NOT NULL, | eye_user_menu varchar(255) CHARACTER SET utf8 NOT NULL,
updated_at datetime NOT NULL, | delete_date date NOT NULL, | unifa_id int NOT NULL,
manage_id varchar(15) CHARACTER SET utf8 NOT NULL, | created_at datetime NOT NULL, | unifa_name varchar(255) CHARACTER SET utf8 NOT NULL,
PRIMARY KEY ("id") | updated_at datetime NOT NULL, | unifa_url text CHARACTER SET utf8 NOT NULL,
); | manage_id varchar(15) CHARACTER SET utf8 NOT NULL | PRIMARY KEY ("id")
| ); | );
CREATE TABLE "eye_sys"."designers_page" (
id bigint NOT NULL, | CREATE TABLE "eye_sys"."news" ( | CREATE TABLE "eye_sys"."site_bilingual Copy 1" (
designers_id bigint NOT NULL, | id bigint NOT NULL, | id bigint NOT NULL,
contents text CHARACTER SET utf8 NOT NULL, | site_type int NOT NULL, | release_id bigint NOT NULL 1,
is_release tinyint NOT NULL, | date datetime NOT NULL, | site_id bigint NOT NULL,
is_check tinyint NOT NULL, | subject varchar(255) CHARACTER SET utf8 NOT NULL, | member_id bigint NOT NULL,
updated_at datetime NOT NULL, | category_id int NOT NULL, | number int NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, | body text CHARACTER SET utf8 NOT NULL, | lang int NOT NULL,
PRIMARY KEY ("id") | is_important tinyint NOT NULL, | url varchar(255) CHARACTER SET utf8 NOT NULL,
); | is_release tinyint NOT NULL, | created_at datetime NOT NULL,
| created_at datetime NOT NULL, | updated_at datetime NOT NULL,
| manage_id int NOT NULL, | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."example_site" ( | PRIMARY KEY ("id") | PRIMARY KEY ("id")
id bigint NOT NULL, | ); | );
name varchar(255) CHARACTER SET utf8 NOT NULL,
url varchar(255) CHARACTER SET utf8 NOT NULL,
category_id int NOT NULL, | CREATE TABLE "eye_sys"."partner" ( | CREATE TABLE "eye_sys"."site_contents Copy 1" (
business_kind int NOT NULL, | id bigint NOT NULL, | id bigint NOT NULL,
tmp_id bigint NOT NULL, | company varchar(255) CHARACTER SET utf8 NOT NULL, | release_id bigint NOT NULL 1,
file varchar(20) CHARACTER SET utf8 NOT NULL, | name varchar(255) CHARACTER SET utf8 NOT NULL, | site_id bigint NOT NULL,
is_release tinyint NOT NULL, | kana varchar(255) CHARACTER SET utf8 NOT NULL, | member_id bigint NOT NULL,
created_at datetime NOT NULL, | tel varchar(20) CHARACTER SET utf8 NOT NULL, | number int NOT NULL,
manage_id varchar(20) CHARACTER SET utf8 NOT NULL, | mail varchar(255) CHARACTER SET utf8 NOT NULL, | number_of_top int NOT NULL,
PRIMARY KEY ("id") | paypal_mail varchar(100) CHARACTER SET utf8 NOT NULL, | child_number int NOT NULL,
); | password varchar(255) CHARACTER SET utf8 NOT NULL, | parent_id bigint NOT NULL,
| zip varchar(10) CHARACTER SET utf8 NOT NULL, | title varchar(255) CHARACTER SET utf8 NOT NULL,
| area int NOT NULL, | dir varchar(255) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."eye_account" ( | address varchar(255) CHARACTER SET utf8 NOT NULL, | type int NOT NULL,
id bigint NOT NULL, | note text CHARACTER SET utf8 NOT NULL, | url text CHARACTER SET utf8 NOT NULL,
auth_code int NOT NULL, | intro_kbn int NOT NULL, | url_is_blank tinyint NOT NULL,
mail varchar(50) CHARACTER SET utf8 NOT NULL, | is_fee tinyint NOT NULL, | nav_name varchar(50) CHARACTER SET utf8 NOT NULL,
password varchar(255) CHARACTER SET utf8 NOT NULL, | is_delete tinyint NOT NULL, | head_title varchar(50) CHARACTER SET utf8 NOT NULL,
device_type int NULL DEFAULT NULL, | is_withdraw tinyint NOT NULL, | head_keywords varchar(255) CHARACTER SET utf8 NOT NULL,
push_token text CHARACTER SET utf8 NULL DEFAULT NULL, | created_at date NOT NULL, | head_description text CHARACTER SET utf8 NOT NULL,
endpoint_arn text CHARACTER SET utf8 NULL DEFAULT NULL, | updated_at datetime NOT NULL, | is_release tinyint NOT NULL,
user_agent text CHARACTER SET utf8 NOT NULL, | manage_id varchar(50) CHARACTER SET utf8 NOT NULL, | created_at datetime NOT NULL,
is_delete tinyint NOT NULL, | PRIMARY KEY ("id") | updated_at datetime NOT NULL,
created_at datetime NOT NULL, | ); | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
updated_at datetime NOT NULL, |  | PRIMARY KEY ("id")
manage_id varchar(255) CHARACTER SET utf8 NOT NULL, |  | );
PRIMARY KEY ("id") | CREATE TABLE "eye_sys"."payment_dispose_flag" (
); | id bigint NOT NULL,
| payment_log_id bigint NOT NULL, | CREATE TABLE "eye_sys"."site_contents_blog Copy 1" (
| dispose_log_id bigint NOT NULL, | id bigint NOT NULL,
CREATE TABLE "eye_sys"."eye_aim" ( | fee_type int NOT NULL, | release_id bigint NOT NULL,
id bigint NOT NULL, | is_dispose tinyint NOT NULL, | member_id bigint NOT NULL,
release_id bigint NOT NULL, | created_at datetime NOT NULL, | site_id bigint NOT NULL,
member_id bigint NOT NULL, | updated_at datetime NOT NULL, | contents_id int NOT NULL,
site_id bigint NOT NULL, | manage_id varchar(15) CHARACTER SET utf8 NOT NULL, | date datetime NOT NULL,
year int NOT NULL, | PRIMARY KEY ("id") | category_id int NOT NULL,
month int NOT NULL, | ); | title varchar(255) CHARACTER SET utf8 NOT NULL,
comment text CHARACTER SET utf8 NOT NULL, |  | body text CHARACTER SET utf8 NOT NULL,
created_at datetime NOT NULL, |  | url varchar(255) CHARACTER SET utf8 NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, | CREATE TABLE "eye_sys"."payment_dispose_log" ( | file varchar(20) CHARACTER SET utf8 NOT NULL,
PRIMARY KEY ("id") | id bigint NOT NULL, | is_facebook tinyint NOT NULL,
); | member_type int NOT NULL, | is_release tinyint NOT NULL,
| member_id bigint NOT NULL, | created_at datetime NOT NULL,
| name varchar(50) CHARACTER SET utf8 NOT NULL, | updated_at datetime NOT NULL,
CREATE TABLE "eye_sys"."eye_album" ( | kana varchar(50) CHARACTER SET utf8 NOT NULL, | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
id bigint NOT NULL, | paypal_mail varchar(50) CHARACTER SET utf8 NOT NULL, | PRIMARY KEY ("id")
release_id bigint NOT NULL, | fee bigint NOT NULL, | );
member_id bigint NOT NULL, | payment_date date NOT NULL,
site_id bigint NOT NULL, | created_at datetime NOT NULL,
number bigint NOT NULL, | manage_id varchar(15) CHARACTER SET utf8 NOT NULL, | CREATE TABLE "eye_sys"."site_contents_category" (
event_id bigint NOT NULL, | PRIMARY KEY ("id") | id bigint NOT NULL,
file text CHARACTER SET utf8 NOT NULL, | ); | release_id bigint NOT NULL,
comment text CHARACTER SET utf8 NOT NULL, |  | member_id bigint NOT NULL,
created_at datetime NOT NULL, |  | site_id bigint NOT NULL,
updated_at datetime NOT NULL, | CREATE TABLE "eye_sys"."payment_log" ( | contents_id int NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, | id bigint NOT NULL, | number bigint NOT NULL,
PRIMARY KEY ("id") | site_id bigint NOT NULL, | title varchar(255) CHARACTER SET utf8 NOT NULL,
); | members_id bigint NOT NULL, | created_at datetime NOT NULL,
| members_name varchar(50) CHARACTER SET utf8 NOT NULL, | updated_at datetime NOT NULL,
| payment_status varchar(255) CHARACTER SET utf8 NOT NULL, | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."eye_album_event" ( | paypal_mail varchar(100) CHARACTER SET utf8 NOT NULL, | PRIMARY KEY ("id")
id bigint NOT NULL, | profit int NOT NULL, | );
release_id bigint NOT NULL, | amount int NOT NULL,
member_id bigint NOT NULL, | payment_fee int NOT NULL,
site_id bigint NOT NULL, | designers_id bigint NOT NULL, | CREATE TABLE "eye_sys"."site_contents_event" (
year year NOT NULL, | designers_fee int NOT NULL, | id bigint NOT NULL,
month int NOT NULL, | intro_type int NOT NULL, | release_id bigint NOT NULL,
name varchar(255) CHARACTER SET utf8 NOT NULL, | intro_id bigint NOT NULL, | member_id bigint NOT NULL,
is_release tinyint NOT NULL, | intro_fee int NOT NULL, | site_id bigint NOT NULL,
is_delete tinyint NOT NULL, | 2nd_intro_type int NOT NULL, | contents_id int NOT NULL,
created_at datetime NOT NULL, | 2nd_intro_id bigint NOT NULL, | date datetime NOT NULL,
updated_at datetime NOT NULL, | 2nd_intro_fee int NOT NULL, | event_date datetime NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, | payment_date datetime NOT NULL, | category_id int NOT NULL,
PRIMARY KEY ("id") | created_at datetime NOT NULL, | title varchar(255) CHARACTER SET utf8 NOT NULL,
); | PRIMARY KEY ("id") | place varchar(255) CHARACTER SET utf8 NOT NULL,
| ); | price varchar(255) CHARACTER SET utf8 NOT NULL,
capacity varchar(255) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."eye_bus_course" ( |  | body text CHARACTER SET utf8 NOT NULL,
id bigint NOT NULL, | CREATE TABLE "eye_sys"."paypal_ipn" ( | url varchar(255) CHARACTER SET utf8 NOT NULL,
release_id bigint NULL DEFAULT NULL, | id bigint NOT NULL, | file varchar(20) CHARACTER SET utf8 NOT NULL,
member_id bigint NULL DEFAULT NULL, | business varchar(50) CHARACTER SET utf8 NOT NULL, | is_facebook tinyint NOT NULL,
site_id bigint NULL DEFAULT NULL, | receiver_email varchar(50) CHARACTER SET utf8 NOT NULL, | is_release tinyint NOT NULL,
number int NULL DEFAULT NULL, | receiver_id varchar(50) CHARACTER SET utf8 NOT NULL, | created_at datetime NOT NULL,
kbn int NULL DEFAULT NULL, | item_name varchar(255) CHARACTER SET utf8 NOT NULL, | updated_at datetime NOT NULL,
name varchar(255) CHARACTER SET utf8 NULL DEFAULT '', | item_number varchar(50) CHARACTER SET utf8 NOT NULL, | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
sort int NULL DEFAULT NULL, | invoice varchar(50) CHARACTER SET utf8 NOT NULL, | PRIMARY KEY ("id")
is_delete tinyint NOT NULL 0, | custom varchar(50) CHARACTER SET utf8 NOT NULL, | );
created_at datetime NULL DEFAULT NULL, | option_name1 varchar(50) CHARACTER SET utf8 NOT NULL,
manage_id varchar(255) CHARACTER SET utf8 NULL DEFAULT '', | option_selection1 varchar(50) CHARACTER SET utf8 NOT NULL,
PRIMARY KEY ("id") | option_name2 varchar(50) CHARACTER SET utf8 NOT NULL, | CREATE TABLE "eye_sys"."site_contents_free" (
); | option_selection2 varchar(50) CHARACTER SET utf8 NOT NULL, | id bigint NOT NULL,
| payment_status varchar(50) CHARACTER SET utf8 NOT NULL, | release_id bigint NOT NULL,
| pending_reason varchar(50) CHARACTER SET utf8 NOT NULL, | member_id bigint NOT NULL,
CREATE TABLE "eye_sys"."eye_bus_stop" ( | reason_code varchar(50) CHARACTER SET utf8 NOT NULL, | site_id bigint NOT NULL,
id bigint NOT NULL, | payment_date varchar(50) CHARACTER SET utf8 NOT NULL, | contents_id int NOT NULL,
release_id bigint NULL DEFAULT NULL, | txn_id varchar(50) CHARACTER SET utf8 NOT NULL, | number bigint NOT NULL,
member_id bigint NULL DEFAULT NULL, | parent_txn_id varchar(50) CHARACTER SET utf8 NOT NULL, | title varchar(255) CHARACTER SET utf8 NOT NULL,
site_id bigint NULL DEFAULT NULL, | txn_type varchar(50) CHARACTER SET utf8 NOT NULL, | body text CHARACTER SET utf8 NOT NULL,
number int NULL DEFAULT NULL, | mc_gross varchar(50) CHARACTER SET utf8 NOT NULL, | is_release tinyint NOT NULL,
kbn int NULL DEFAULT NULL, | mc_fee varchar(50) CHARACTER SET utf8 NOT NULL, | created_at datetime NOT NULL,
course_id int NULL DEFAULT NULL, | mc_currency varchar(50) CHARACTER SET utf8 NOT NULL, | updated_at datetime NOT NULL,
name varchar(255) CHARACTER SET utf8 NULL DEFAULT '', | settle_amount varchar(50) CHARACTER SET utf8 NOT NULL, | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
latitude decimal(9,6) NULL DEFAULT NULL, | exchange_rate varchar(50) CHARACTER SET utf8 NOT NULL, | PRIMARY KEY ("id")
longitude decimal(9,6) NULL DEFAULT NULL, | payment_gross varchar(50) CHARACTER SET utf8 NOT NULL, | );
sort int NULL DEFAULT NULL, | payment_fee varchar(50) CHARACTER SET utf8 NOT NULL,
time1 time NULL DEFAULT NULL, | first_name varchar(50) CHARACTER SET utf8 NOT NULL,
time2 time NULL DEFAULT NULL, | last_name varchar(50) CHARACTER SET utf8 NOT NULL, | CREATE TABLE "eye_sys"."site_contents_gallery" (
time3 time NULL DEFAULT NULL, | payer_business_name varchar(50) CHARACTER SET utf8 NOT NULL, | id bigint NOT NULL,
time4 time NULL DEFAULT NULL, | address_name varchar(50) CHARACTER SET utf8 NOT NULL, | release_id bigint NOT NULL,
time5 time NULL DEFAULT NULL, | address_street varchar(50) CHARACTER SET utf8 NOT NULL, | member_id bigint NOT NULL,
is_delete tinyint NOT NULL 0, | address_city varchar(50) CHARACTER SET utf8 NOT NULL, | site_id bigint NOT NULL,
created_at datetime NULL DEFAULT NULL, | address_state varchar(50) CHARACTER SET utf8 NOT NULL, | contents_id int NOT NULL,
manage_id varchar(255) CHARACTER SET utf8 NULL DEFAULT '', | address_zip varchar(50) CHARACTER SET utf8 NOT NULL, | number bigint NOT NULL,
PRIMARY KEY ("id") | address_country varchar(50) CHARACTER SET utf8 NOT NULL, | title varchar(255) CHARACTER SET utf8 NOT NULL,
); | payer_email varchar(50) CHARACTER SET utf8 NOT NULL, | category_id int NOT NULL,
| payer_id varchar(50) CHARACTER SET utf8 NOT NULL, | comment text CHARACTER SET utf8 NOT NULL,
| payer_status varchar(50) CHARACTER SET utf8 NOT NULL, | file text CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."eye_category" ( | payment_type varchar(50) CHARACTER SET utf8 NOT NULL, | is_release tinyint NOT NULL,
id bigint NOT NULL, | subscr_date varchar(50) CHARACTER SET utf8 NOT NULL, | created_at datetime NOT NULL,
release_id bigint NOT NULL, | subscr_effective varchar(50) CHARACTER SET utf8 NOT NULL, | updated_at datetime NOT NULL,
member_id bigint NOT NULL, | period1 varchar(50) CHARACTER SET utf8 NOT NULL, | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
site_id bigint NOT NULL, | period2 varchar(50) CHARACTER SET utf8 NOT NULL, | PRIMARY KEY ("id")
table_id int NOT NULL, | period3 varchar(50) CHARACTER SET utf8 NOT NULL, | );
number bigint NOT NULL, | amount1 varchar(50) CHARACTER SET utf8 NOT NULL,
title varchar(255) CHARACTER SET utf8 NOT NULL, | amount2 varchar(50) CHARACTER SET utf8 NOT NULL,
created_at datetime NOT NULL, | amount3 varchar(50) CHARACTER SET utf8 NOT NULL, | CREATE TABLE "eye_sys"."site_contents_images" (
updated_at datetime NOT NULL, | mc_amount1 varchar(50) CHARACTER SET utf8 NOT NULL, | id bigint NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, | mc_amount2 varchar(50) CHARACTER SET utf8 NOT NULL, | release_id bigint NOT NULL,
PRIMARY KEY ("id") | recurring varchar(50) CHARACTER SET utf8 NOT NULL, | member_id bigint NOT NULL,
); | reattempt varchar(50) CHARACTER SET utf8 NOT NULL, | site_id bigint NOT NULL,
| retry_at varchar(50) CHARACTER SET utf8 NOT NULL, | contents_id int NOT NULL,
| recur_times varchar(50) CHARACTER SET utf8 NOT NULL, | parent_id bigint NOT NULL,
CREATE TABLE "eye_sys"."eye_consumption" ( | username varchar(50) CHARACTER SET utf8 NOT NULL, | number bigint NOT NULL,
id int NOT NULL, | password varchar(50) CHARACTER SET utf8 NOT NULL, | title varchar(255) CHARACTER SET utf8 NOT NULL,
user_id int NULL DEFAULT NULL, | subscr_id varchar(50) CHARACTER SET utf8 NOT NULL, | file varchar(50) CHARACTER SET utf8 NOT NULL,
product_id int NULL DEFAULT NULL, | created_at datetime NOT NULL, | is_release tinyint NOT NULL,
unit_price int NULL DEFAULT NULL, | PRIMARY KEY ("id") | created_at datetime NOT NULL,
incruding_tax int NULL DEFAULT NULL, | ); | updated_at datetime NOT NULL,
tax_rate float NULL DEFAULT NULL, |  | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
number int NULL DEFAULT NULL, |  | PRIMARY KEY ("id")
checked tinyint NULL DEFAULT NULL, | CREATE TABLE "eye_sys"."receipt" ( | );
created_at datetime NULL DEFAULT NULL, | id bigint NOT NULL,
updated_at datetime NULL DEFAULT NULL, | year int NOT NULL,
PRIMARY KEY ("id") | month int NOT NULL, | CREATE TABLE "eye_sys"."site_contents_menu" (
); | member_type int NOT NULL, | id bigint NOT NULL,
| member_id bigint NOT NULL, | release_id bigint NOT NULL,
| peypal_account varchar(50) CHARACTER SET utf8 NOT NULL, | member_id bigint NOT NULL,
CREATE TABLE "eye_sys"."eye_contact" ( | price bigint NOT NULL, | site_id bigint NOT NULL,
id bigint NOT NULL, | date date NOT NULL, | contents_id int NOT NULL,
release_id bigint NOT NULL, | created_at datetime NOT NULL, | number bigint NOT NULL,
member_id bigint NOT NULL, | updated_at datetime NOT NULL, | title varchar(255) CHARACTER SET utf8 NOT NULL,
site_id bigint NOT NULL, | manage_id varchar(50) CHARACTER SET utf8 NOT NULL, | category_id int NOT NULL,
from_id bigint NOT NULL, | PRIMARY KEY ("id") | price varchar(255) CHARACTER SET utf8 NOT NULL,
to_ids text CHARACTER SET utf8 NOT NULL, | ); | price_note varchar(255) CHARACTER SET utf8 NOT NULL,
comment text CHARACTER SET utf8 NOT NULL, |  | file text CHARACTER SET utf8 NOT NULL,
confirm_user text CHARACTER SET utf8 NOT NULL, |  | comment text CHARACTER SET utf8 NOT NULL,
updater_type int NOT NULL, | CREATE TABLE "eye_sys"."setting" ( | detail text CHARACTER SET utf8 NOT NULL,
updater_id bigint NOT NULL, | id int NOT NULL, | link_url text CHARACTER SET utf8 NOT NULL,
created_at datetime NOT NULL, | label varchar(255) CHARACTER SET utf8 NOT NULL, | link_text varchar(255) CHARACTER SET utf8 NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, | element varchar(255) CHARACTER SET utf8 NOT NULL, | is_pickup tinyint NOT NULL,
PRIMARY KEY ("id") | type varchar(50) CHARACTER SET utf8 NOT NULL, | is_release tinyint NOT NULL,
); | value text CHARACTER SET utf8 NOT NULL, | created_at datetime NOT NULL,
| PRIMARY KEY ("id") | updated_at datetime NOT NULL,
| ); | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."eye_entering" ( |  | PRIMARY KEY ("id")
id int NOT NULL, |  | );
member_id bigint NULL 0,
site_id int NOT NULL,
user_id int NOT NULL 0, |  | CREATE TABLE "eye_sys"."site_contents_shop" (
entering_at datetime NULL DEFAULT NULL, |  | id bigint NOT NULL,
leaving_at datetime NULL DEFAULT NULL, |  | release_id bigint NOT NULL,
over_time_fee int NULL 0, |  | member_id bigint NOT NULL,
absent_reason int NULL DEFAULT NULL, |  | site_id bigint NOT NULL,
created_ymd int NOT NULL 0, |  | contents_id int NOT NULL,
created_at datetime NULL DEFAULT NULL, |  | number bigint NOT NULL,
PRIMARY KEY ("id") |  | title varchar(255) CHARACTER SET utf8 NOT NULL,
); |  | comment text CHARACTER SET utf8 NOT NULL,
file1 varchar(20) CHARACTER SET utf8 NOT NULL,
file2 varchar(20) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."eye_mail_fixed" ( |  | tel varchar(255) CHARACTER SET utf8 NOT NULL,
id bigint NOT NULL, |  | fax varchar(255) CHARACTER SET utf8 NOT NULL,
release_id bigint NOT NULL, |  | opening_hours varchar(255) CHARACTER SET utf8 NOT NULL,
member_id bigint NOT NULL, |  | holiday varchar(255) CHARACTER SET utf8 NOT NULL,
site_id bigint NOT NULL, |  | address varchar(255) CHARACTER SET utf8 NOT NULL,
name varchar(255) CHARACTER SET utf8 NOT NULL, |  | address_map varchar(255) CHARACTER SET utf8 NOT NULL,
subject varchar(255) CHARACTER SET utf8 NOT NULL, |  | lat varchar(255) CHARACTER SET utf8 NOT NULL,
body text CHARACTER SET utf8 NOT NULL, |  | lng varchar(255) CHARACTER SET utf8 NOT NULL,
created_at datetime NOT NULL, |  | access text CHARACTER SET utf8 NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, |  | parking varchar(255) CHARACTER SET utf8 NOT NULL,
PRIMARY KEY ("id") |  | note text CHARACTER SET utf8 NOT NULL,
); |  | is_release tinyint NOT NULL,
created_at datetime NOT NULL,
updated_at datetime NOT NULL,
CREATE TABLE "eye_sys"."eye_mail_log" ( |  | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
id bigint NOT NULL, |  | PRIMARY KEY ("id")
release_id bigint NOT NULL, |  | );
member_id bigint NOT NULL,
site_id bigint NOT NULL,
date_time datetime NOT NULL, |  | CREATE TABLE "eye_sys"."site_contents_table" (
subject varchar(255) CHARACTER SET utf8 NOT NULL, |  | id bigint NOT NULL,
body text CHARACTER SET utf8 NOT NULL, |  | release_id bigint NOT NULL,
is_confirm_check tinyint NOT NULL, |  | member_id bigint NOT NULL,
is_send_teacher tinyint NOT NULL, |  | site_id bigint NOT NULL,
send_count bigint NOT NULL, |  | contents_id int NOT NULL,
is_reservation tinyint NOT NULL 0, |  | number bigint NOT NULL,
first_send_date datetime NOT NULL, |  | title varchar(255) CHARACTER SET utf8 NOT NULL,
created_at datetime NOT NULL, |  | value text CHARACTER SET utf8 NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, |  | is_release tinyint NOT NULL,
PRIMARY KEY ("id") |  | created_at datetime NOT NULL,
); |  | updated_at datetime NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
PRIMARY KEY ("id")
CREATE TABLE "eye_sys"."eye_mail_sendto" ( |  | );
id bigint NOT NULL,
release_id bigint NOT NULL,
member_id bigint NOT NULL, |  | CREATE TABLE "eye_sys"."site_facebook" (
site_id bigint NOT NULL, |  | id bigint NOT NULL,
log_id bigint NOT NULL, |  | release_id bigint NOT NULL,
mail varchar(255) CHARACTER SET utf8 NOT NULL, |  | site_id bigint NOT NULL,
is_confirm tinyint NOT NULL, |  | member_id bigint NOT NULL,
confirm_date datetime NOT NULL, |  | number int NOT NULL,
confirm_place varchar(255) CHARACTER SET utf8 NOT NULL, |  | title varchar(255) CHARACTER SET utf8 NOT NULL,
kbn bigint NOT NULL, |  | facebook_ID varchar(255) CHARACTER SET utf8 NOT NULL,
to_table_id int NOT NULL, |  | created_at datetime NOT NULL,
to_id bigint NOT NULL, |  | updated_at datetime NOT NULL,
status int NOT NULL, |  | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
send_count int NOT NULL, |  | PRIMARY KEY ("id")
is_reservation tinyint NOT NULL 0, |  | );
endpoint_arn text CHARACTER SET utf8 NOT NULL,
created_at datetime NOT NULL,
updated_at datetime NOT NULL, |  | CREATE TABLE "eye_sys"."site_make_page" (
PRIMARY KEY ("id") |  | id bigint NOT NULL,
); |  | release_id bigint NOT NULL 1,
site_id bigint NOT NULL,
member_id bigint NOT NULL,
CREATE TABLE "eye_sys"."eye_manager" ( |  | subject varchar(255) CHARACTER SET utf8 NOT NULL,
id int NOT NULL 0, |  | body text CHARACTER SET utf8 NOT NULL,
release_id int NOT NULL, |  | created_at datetime NOT NULL,
member_id bigint NOT NULL, |  | updated_at datetime NOT NULL,
site_id bigint NOT NULL, |  | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
name varchar(50) CHARACTER SET utf8 NOT NULL, |  | PRIMARY KEY ("id")
mail varchar(255) CHARACTER SET utf8 NOT NULL, |  | );
password varchar(255) CHARACTER SET utf8 NOT NULL,
kbn varchar(255) CHARACTER SET utf8 NOT NULL,
pages varchar(255) CHARACTER SET utf8 NOT NULL, |  | CREATE TABLE "eye_sys"."site_mmg_log" (
is_delete tinyint NOT NULL, |  | id bigint NOT NULL,
created_at datetime NOT NULL '0000-00-00 00:00:00', |  | release_id bigint NOT NULL,
updated_at datetime NOT NULL '0000-00-00 00:00:00', |  | member_id bigint NOT NULL,
PRIMARY KEY ("id") |  | site_id bigint NOT NULL,
); |  | subject varchar(255) CHARACTER SET utf8 NOT NULL,
body text CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."designers_news" ( |  | send_count bigint NOT NULL,
id bigint NOT NULL, |  | created_at datetime NOT NULL,
date datetime NOT NULL, |  | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
comment text CHARACTER SET utf8 NOT NULL, |  | PRIMARY KEY ("id")
link varchar(255) CHARACTER SET utf8 NOT NULL, |  | );
is_release tinyint NOT NULL,
created_at datetime NOT NULL,
updated_at datetime NOT NULL, |  | CREATE TABLE "eye_sys"."site_mmg_sendto" (
manage_id varchar(15) CHARACTER SET utf8 NOT NULL, |  | id bigint NOT NULL,
PRIMARY KEY ("id") |  | member_id bigint NOT NULL,
); |  | site_id bigint NOT NULL,
log_id bigint NOT NULL,
mail varchar(255) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."designers_page" ( |  | mmg_user_id bigint NOT NULL,
id bigint NOT NULL, |  | created_at datetime NOT NULL,
designers_id bigint NOT NULL, |  | PRIMARY KEY ("id")
contents text CHARACTER SET utf8 NOT NULL, |  | );
is_release tinyint NOT NULL,
is_check tinyint NOT NULL,
updated_at datetime NOT NULL, |  | CREATE TABLE "eye_sys"."site_mmg_tmp" (
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, |  | id bigint NOT NULL,
PRIMARY KEY ("id") |  | release_id int NOT NULL,
); |  | member_id bigint NOT NULL,
site_id bigint NOT NULL,
subject varchar(255) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."example_site" ( |  | body text CHARACTER SET utf8 NOT NULL,
id bigint NOT NULL, |  | created_at datetime NOT NULL,
name varchar(255) CHARACTER SET utf8 NOT NULL, |  | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
url varchar(255) CHARACTER SET utf8 NOT NULL, |  | PRIMARY KEY ("id")
category_id int NOT NULL, |  | );
business_kind int NOT NULL,
tmp_id bigint NOT NULL,
file varchar(20) CHARACTER SET utf8 NOT NULL, |  | CREATE TABLE "eye_sys"."site_mmg_user" (
is_release tinyint NOT NULL, |  | id bigint NOT NULL,
created_at datetime NOT NULL, |  | release_id bigint NOT NULL,
manage_id varchar(20) CHARACTER SET utf8 NOT NULL, |  | member_id bigint NOT NULL,
PRIMARY KEY ("id") |  | site_id bigint NOT NULL,
); |  | mail varchar(255) CHARACTER SET utf8 NOT NULL,
tel varchar(20) CHARACTER SET utf8 NOT NULL,
name varchar(255) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."eye_account" ( |  | kana varchar(255) CHARACTER SET utf8 NOT NULL,
id bigint NOT NULL, |  | sex int NOT NULL,
auth_code int NOT NULL, |  | birthday date NOT NULL,
mail varchar(50) CHARACTER SET utf8 NOT NULL, |  | zip varchar(50) CHARACTER SET utf8 NOT NULL,
password varchar(255) CHARACTER SET utf8 NOT NULL, |  | area int NOT NULL,
device_type int NULL DEFAULT NULL, |  | address varchar(255) CHARACTER SET utf8 NOT NULL,
push_token text CHARACTER SET utf8 NULL DEFAULT NULL, |  | password varchar(255) CHARACTER SET utf8 NOT NULL,
endpoint_arn text CHARACTER SET utf8 NULL DEFAULT NULL, |  | created_at datetime NOT NULL,
user_agent text CHARACTER SET utf8 NOT NULL, |  | manage_id varchar(255) CHARACTER SET utf8 NOT NULL,
is_delete tinyint NOT NULL, |  | PRIMARY KEY ("id")
created_at datetime NOT NULL, |  | );
updated_at datetime NOT NULL,
manage_id varchar(255) CHARACTER SET utf8 NOT NULL,
PRIMARY KEY ("id") |  | CREATE TABLE "eye_sys"."site_option" (
); |  | id bigint NOT NULL,
site_id bigint NOT NULL,
member_id bigint NOT NULL,
CREATE TABLE "eye_sys"."eye_aim" ( |  | option_id int NOT NULL,
id bigint NOT NULL, |  | PRIMARY KEY ("id")
release_id bigint NOT NULL, |  | );
member_id bigint NOT NULL,
site_id bigint NOT NULL,
year int NOT NULL, |  | CREATE TABLE "eye_sys"."site_setting" (
month int NOT NULL, |  | id bigint NOT NULL,
comment text CHARACTER SET utf8 NOT NULL, |  | site_id bigint NOT NULL,
created_at datetime NOT NULL, |  | member_id bigint NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, |  | kbn int NOT NULL,
PRIMARY KEY ("id") |  | field varchar(255) CHARACTER SET utf8 NOT NULL,
); |  | value text CHARACTER SET utf8 NOT NULL,
created_at datetime NOT NULL,
updated_at int NOT NULL,
CREATE TABLE "eye_sys"."eye_album" ( |  | manage_id varchar(255) CHARACTER SET utf8 NOT NULL,
id bigint NOT NULL, |  | PRIMARY KEY ("id")
release_id bigint NOT NULL, |  | );
member_id bigint NOT NULL,
site_id bigint NOT NULL,
number bigint NOT NULL, |  | CREATE TABLE "eye_sys"."site_slide" (
event_id bigint NOT NULL, |  | id bigint NOT NULL,
file text CHARACTER SET utf8 NOT NULL, |  | release_id bigint NOT NULL,
comment text CHARACTER SET utf8 NOT NULL, |  | member_id bigint NOT NULL,
created_at datetime NOT NULL, |  | site_id bigint NOT NULL,
updated_at datetime NOT NULL, |  | number bigint NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, |  | subject varchar(255) CHARACTER SET utf8 NOT NULL,
PRIMARY KEY ("id") |  | link text CHARACTER SET utf8 NOT NULL,
); |  | is_blank tinyint NOT NULL,
file text CHARACTER SET utf8 NOT NULL,
is_release tinyint NOT NULL,
CREATE TABLE "eye_sys"."eye_album_event" ( |  | created_at datetime NOT NULL,
id bigint NOT NULL, |  | updated_at datetime NOT NULL,
release_id bigint NOT NULL, |  | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
member_id bigint NOT NULL, |  | PRIMARY KEY ("id")
site_id bigint NOT NULL, |  | );
year year NOT NULL,
month int NOT NULL,
name varchar(255) CHARACTER SET utf8 NOT NULL, |  | CREATE TABLE "eye_sys"."site_top" (
is_release tinyint NOT NULL, |  | id bigint NOT NULL,
is_delete tinyint NOT NULL, |  | release_id bigint NOT NULL 1,
created_at datetime NOT NULL, |  | site_id bigint NOT NULL,
updated_at datetime NOT NULL, |  | member_id bigint NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, |  | number int NOT NULL,
PRIMARY KEY ("id") |  | contents_id int NOT NULL,
); |  | contents_type int NOT NULL,
top_limit int NOT NULL,
subject varchar(255) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."eye_bus_course" ( |  | body text CHARACTER SET utf8 NOT NULL,
id bigint NOT NULL, |  | width int NOT NULL 100,
release_id bigint NULL DEFAULT NULL, |  | is_release tinyint NOT NULL,
member_id bigint NULL DEFAULT NULL, |  | created_at datetime NOT NULL,
site_id bigint NULL DEFAULT NULL, |  | updated_at datetime NOT NULL,
number int NULL DEFAULT NULL, |  | manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
kbn int NULL DEFAULT NULL, |  | PRIMARY KEY ("id")
name varchar(255) CHARACTER SET utf8 NULL DEFAULT '', |  | );
sort int NULL DEFAULT NULL,
is_delete tinyint NOT NULL 0,
created_at datetime NULL DEFAULT NULL, |  | CREATE TABLE "eye_sys"."support_info" (
manage_id varchar(255) CHARACTER SET utf8 NULL DEFAULT '', |  | id bigint NOT NULL,
PRIMARY KEY ("id") |  | member_type int NOT NULL,
); |  | member_id bigint NOT NULL,
site_id bigint NOT NULL,
category_id int NOT NULL,
CREATE TABLE "eye_sys"."eye_bus_stop" ( |  | number bigint NOT NULL,
id bigint NOT NULL, |  | comment text CHARACTER SET utf8 NOT NULL,
release_id bigint NULL DEFAULT NULL, |  | is_release tinyint NOT NULL,
member_id bigint NULL DEFAULT NULL, |  | status int NOT NULL,
site_id bigint NULL DEFAULT NULL, |  | created_at datetime NOT NULL,
number int NULL DEFAULT NULL, |  | updated_at datetime NOT NULL,
kbn int NULL DEFAULT NULL, |  | manage_id varchar(15) CHARACTER SET utf8 NOT NULL,
course_id int NULL DEFAULT NULL, |  | PRIMARY KEY ("id")
name varchar(255) CHARACTER SET utf8 NULL DEFAULT '', |  | );
latitude decimal(9,6) NULL DEFAULT NULL,
longitude decimal(9,6) NULL DEFAULT NULL,
sort int NULL DEFAULT NULL, |  | CREATE TABLE "eye_sys"."template" (
time1 time NULL DEFAULT NULL, |  | id bigint NOT NULL,
time2 time NULL DEFAULT NULL, |  | designers_id varchar(8) CHARACTER SET utf8 NOT NULL,
time3 time NULL DEFAULT NULL, |  | file varchar(50) CHARACTER SET utf8 NOT NULL,
time4 time NULL DEFAULT NULL, |  | file_sp varchar(50) CHARACTER SET utf8 NOT NULL,
time5 time NULL DEFAULT NULL, |  | keyword varchar(255) CHARACTER SET utf8 NOT NULL,
is_delete tinyint NOT NULL 0, |  | is_gb_pickup tinyint NOT NULL,
created_at datetime NULL DEFAULT NULL, |  | is_gbd_pickup tinyint NOT NULL,
manage_id varchar(255) CHARACTER SET utf8 NULL DEFAULT '', |  | is_release tinyint NOT NULL,
PRIMARY KEY ("id") |  | is_delete tinyint NOT NULL,
); |  | is_confirm tinyint NOT NULL,
delete_date datetime NOT NULL,
created_at datetime NOT NULL,
CREATE TABLE "eye_sys"."eye_category" ( |  | updated_at datetime NOT NULL,
id bigint NOT NULL, |  | manage_id varchar(15) CHARACTER SET utf8 NOT NULL,
release_id bigint NOT NULL, |  | PRIMARY KEY ("id")
member_id bigint NOT NULL, |  | );
site_id bigint NOT NULL,
table_id int NOT NULL,
number bigint NOT NULL, |  | CREATE TABLE "eye_sys"."template_application" (
title varchar(255) CHARACTER SET utf8 NOT NULL, |  | id int NOT NULL,
created_at datetime NOT NULL, |  | designers_id bigint NOT NULL,
updated_at datetime NOT NULL, |  | category int NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, |  | file varchar(20) CHARACTER SET utf8 NOT NULL,
PRIMARY KEY ("id") |  | status int NOT NULL,
); |  | created_at datetime NOT NULL,
updated_at datetime NOT NULL,
manage_id varchar(15) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."eye_consumption" ( |  | PRIMARY KEY ("id")
id int NOT NULL, |  | );
user_id int NULL DEFAULT NULL,
product_id int NULL DEFAULT NULL,
unit_price int NULL DEFAULT NULL, |  | CREATE TABLE "eye_sys"."template_category" (
incruding_tax int NULL DEFAULT NULL, |  | id int NOT NULL,
tax_rate float NULL DEFAULT NULL, |  | number int NOT NULL,
number int NULL DEFAULT NULL, |  | parent_id int NOT NULL,
checked tinyint NULL DEFAULT NULL, |  | name varchar(50) CHARACTER SET utf8 NOT NULL,
created_at datetime NULL DEFAULT NULL, |  | page_url varchar(255) CHARACTER SET utf8 NOT NULL,
updated_at datetime NULL DEFAULT NULL, |  | level int NOT NULL,
PRIMARY KEY ("id") |  | is_release tinyint NOT NULL,
); |  | created_at datetime NOT NULL,
updated_at datetime NOT NULL,
manage_id varchar(15) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."eye_contact" ( |  | PRIMARY KEY ("id")
id bigint NOT NULL, |  | );
release_id bigint NOT NULL,
member_id bigint NOT NULL,
site_id bigint NOT NULL, |  | CREATE TABLE "eye_sys"."topics" (
from_id bigint NOT NULL, |  | id bigint NOT NULL,
to_ids text CHARACTER SET utf8 NOT NULL, |  | category_id int NOT NULL,
comment text CHARACTER SET utf8 NOT NULL, |  | message text CHARACTER SET utf8 NOT NULL,
confirm_user text CHARACTER SET utf8 NOT NULL, |  | picture varchar(255) CHARACTER SET utf8 NOT NULL,
updater_type int NOT NULL, |  | link varchar(255) CHARACTER SET utf8 NOT NULL,
updater_id bigint NOT NULL, |  | name varchar(255) CHARACTER SET utf8 NOT NULL,
created_at datetime NOT NULL, |  | caption varchar(255) CHARACTER SET utf8 NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL, |  | description text CHARACTER SET utf8 NOT NULL,
PRIMARY KEY ("id") |  | is_release tinyint NOT NULL,
); |  | created_at datetime NOT NULL,
updated_at datetime NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
CREATE TABLE "eye_sys"."eye_entering" ( |  | PRIMARY KEY ("id")
id int NOT NULL, |  | );
member_id bigint NULL 0,
site_id int NOT NULL,
user_id int NOT NULL 0, |  | CREATE TABLE "eye_sys"."withdraw_comment" (
entering_at datetime NULL DEFAULT NULL, |  | id bigint NOT NULL,
leaving_at datetime NULL DEFAULT NULL, |  | member_id bigint NOT NULL,
over_time_fee int NULL 0, |  | member_type int NOT NULL,
absent_reason int NULL DEFAULT NULL, |  | comment text CHARACTER SET utf8 NOT NULL,
created_ymd int NOT NULL 0, |  | created_at datetime NOT NULL,
created_at datetime NULL DEFAULT NULL, |  | PRIMARY KEY ("id")
PRIMARY KEY ("id") |  | );
);
CREATE TABLE "eye_sys"."eye_mail_fixed" (
id bigint NOT NULL,
release_id bigint NOT NULL,
member_id bigint NOT NULL,
site_id bigint NOT NULL,
name varchar(255) CHARACTER SET utf8 NOT NULL,
subject varchar(255) CHARACTER SET utf8 NOT NULL,
body text CHARACTER SET utf8 NOT NULL,
created_at datetime NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
PRIMARY KEY ("id")
);
CREATE TABLE "eye_sys"."eye_mail_log" (
id bigint NOT NULL,
release_id bigint NOT NULL,
member_id bigint NOT NULL,
site_id bigint NOT NULL,
date_time datetime NOT NULL,
subject varchar(255) CHARACTER SET utf8 NOT NULL,
body text CHARACTER SET utf8 NOT NULL,
is_confirm_check tinyint NOT NULL,
is_send_teacher tinyint NOT NULL,
send_count bigint NOT NULL,
is_reservation tinyint NOT NULL 0,
first_send_date datetime NOT NULL,
created_at datetime NOT NULL,
manage_id varchar(50) CHARACTER SET utf8 NOT NULL,
PRIMARY KEY ("id")
);
CREATE TABLE "eye_sys"."eye_mail_sendto" (
id bigint NOT NULL,
release_id bigint NOT NULL,
member_id bigint NOT NULL,
site_id bigint NOT NULL,
log_id bigint NOT NULL,
mail varchar(255) CHARACTER SET utf8 NOT NULL,
is_confirm tinyint NOT NULL,
confirm_date datetime NOT NULL,
confirm_place varchar(255) CHARACTER SET utf8 NOT NULL,
kbn bigint NOT NULL,
to_table_id int NOT NULL,
to_id bigint NOT NULL,
status int NOT NULL,
send_count int NOT NULL,
is_reservation tinyint NOT NULL 0,
endpoint_arn text CHARACTER SET utf8 NOT NULL,
created_at datetime NOT NULL,
updated_at datetime NOT NULL,
PRIMARY KEY ("id")
);
CREATE TABLE "eye_sys"."eye_manager" (
id int NOT NULL 0,
release_id int NOT NULL,
member_id bigint NOT NULL,
site_id bigint NOT NULL,
name varchar(50) CHARACTER SET utf8 NOT NULL,
mail varchar(255) CHARACTER SET utf8 NOT NULL,
password varchar(255) CHARACTER SET utf8 NOT NULL,
kbn varchar(255) CHARACTER SET utf8 NOT NULL,
pages varchar(255) CHARACTER SET utf8 NOT NULL,
is_delete tinyint NOT NULL,
created_at datetime NOT NULL '0000-00-00 00:00:00',
updated_at datetime NOT NULL '0000-00-00 00:00:00',
PRIMARY KEY ("id")
);